## Sheet1
PROCUREMENT PLAN
Project Contract No. |  |  | IPA /2021/429-426
Project Title / Acronym: |  |  | Krusevo and Elbasan - acknowledged tourism CB destination
CBC Programme |  |  | Cross-border Programme the Republic of North Macedonia - Republic of Albania under the Instrument of Pre-accession Assistance (IPA II) allocations for 2018 – 2020
Total budget |  |  | 744,930.78
No. | Project Partner (PP) | WORKS |  |  |  | SERVICES |  |  |  | SUPPLIES |  |  |  | Provisional Launching Time (month) | Provisional Contracting Time (month) | NOTES
|  | Description | Budget line(s) charged | Amount budgeted (in EURO) | % of the overall project budget | Description | Budget line(s) charged | Amount budgeted (in EURO) | % of the overall project budget | Description | Budget line(s) charged | Amount budgeted (in EURO) | % of the overall project budget
1 | Krusevo Municipality | [8 empty] | 6.7 Projector for Paragliding Center | 6.7 | 1500 | 0.2014% | mid April 2022 | end of May 2022 | Budget lines will be procured within one procurement call, Single procedure (under 20,000 EUR)
[10 empty] | 6.8 PC / Lap top for the Paragliding Center | 6.8 | 2000 | 0.2685%
[10 empty] | 6.9 Photo camera *1 for the Paragliding Center | 6.9 | 1000 | 0.1342%
[10 empty] | 6.10 Multifunctional all-in-one printer /copier, scanner | 6.10 | 1500 | 0.2014%
2 | Krusevo Municipality |  |  |  |  | 6.3 Independent supervision company ~5% for construction works | 6.3 | 5500 | 0.7383% |  |  |  |  | mid April 2022 | end of May 2022 | Budget line will be procured within one procurement call, Single procedure (under 20,000 EUR)
3 | Krusevo Municipality | 6.1 Infrastructure works Krusevo - Construction of the Approaching site to the Paragliding centre in Krushevo - Supporting wall, Ground works, Final levelling, Gravel layer, Horticulture arrangement | 6.1 | 90000 | 12.08% | [8 empty] | end of April 2022 | begining of June 2022 | This procurment procedure call is under (Simplified procedure, under 100,000 EUR)
4 | Krusevo Municipality |  |  |  |  | 6.6 Building and arranging one urban-downhill cycle route in Krusevo | 6.6 | 40000 | 5.37% |  |  |  |  | beginning of May 2022 | begining of June 2022 | This procurment procedure call is under (Simplified procedure, under 100,000 EUR)
5 | Krusevo Municipality | [8 empty] | 6.4 Two (2) digitised air quality*, wind speed and direction measurement stations | 6.4 | 10000 | 1.342% | begining of June 2022 | beginning of July 2022 | Budget line will be procured within one procurement call (under 20,000 EUR)
6 | Krusevo Municipality | [8 empty] | 6.5 Public Lightening of the town of Krushevo | 6,5 | 40000 | 5.37% | begining of June 2022 | beginning of July 2022 | This procurment procedure call is under (Simplified procedure, under 100,000 EUR)
7 | Krusevo Municipality | [8 empty] | 6.2 Urban equipment, Info stand/cabin point, benches, Arranging terrain for retailers and spectators | 6.2 | 25000 | 3.356% | mid April 2023 | mid May 2023 | This procurment procedure call is under (Simplified procedure, under 100,000 EUR)

## Compatibility Report
Compatibility Report for T_Procurement Plan_KE2.xls
Run on 2/2/2022 16:53
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 115 | Excel 97-2003